## Roadmap
MLOps Project Timeline — AI-Based Accessibility Assistant (JEE Tutor)
Theme 28 ¦ SDG 4 & 10 ¦ AI252TA — Machine Learning Operations ¦ Semester V
Duration: 10 weeks ¦ Start: 21/09/2026 (Monday) ¦ End: 29/11/2026 (Sunday)
Phase 1 — Development & Reproducibility (Weeks 1-4: 21/09 - 18/10)
Weeks 1-2 are corpus work: acquire and document NCERT/PYQ sources, clean and language-tag, and get Git + DVC standing before any data is touched so versioning isn't retrofitted. Week 3 is the experimentation setup — chunking strategies, the synthetic query set that becomes your evaluation ground truth, MLflow conventions. Week 4 is the core ML comparison across multilingual embedding models, the optional intent classifier, and the first working RAG harness.
Phase 2 — Productionization & Deployment (Weeks 5-7: 19/10 - 08/11)
Registry and FastAPI service come first so there's something to test against. Testing and risk checks run in parallel with Dockerization through Week 6. Week 7 is CI/CD and getting a live endpoint with a smoke test — deploy by 08/11 so Phase 3 has a real service to observe.
Phase 3 — Monitoring, Feedback & Governance (Weeks 8-10: 09/11 - 29/11)
Logging and Evidently first, dashboard next, then the deliberate drift experiment in Week 9 with enough runway to complete the detect → retrain → compare → redeploy loop by Week 10. The model card runs alongside from Week 9 since its content comes out of Phase 2's risk checks and Phase 3's per-language metrics.
Critical path
dataset → chunks → embedding experiments → registered model → deployed API → drift experiment. Anything that slips before 18/10 compresses the drift demo, which is your highest-visibility deliverable.
Notes
Two things worth deciding now: the schedule has no built-in slack, so if you want an 8-week version cut the intent classifier and one of the two vector stores rather than shortening Phase 3. And build the baseline traffic window (14/11 - 18/11) with clean data before injecting drift — Evidently needs an uncontaminated reference distribution or the detection story won't be convincing to the evaluators.

## Timeline
Task | Phase | Start Date | End Date | Duration (days) | Week | Assigned to
Dataset acquisition, provenance & ethics/approval note | Phase 1 — Development & Reproducibility | 2026-09-21 | 2026-09-27 | 7 | W1 | Shrey, Shreesha
Git repo scaffold, project structure, README, DVC init | Phase 1 — Development & Reproducibility | 2026-09-21 | 2026-09-25 | 5 | W1 | Shraddha
Data cleaning, language tagging & exploratory analysis | Phase 1 — Development & Reproducibility | 2026-09-26 | 2026-10-04 | 9 | W1 | Shraddha, Shreyank
Chunking strategy experiments + metadata enrichment (LaTeX/MathML) | Phase 1 — Development & Reproducibility | 2026-10-02 | 2026-10-08 | 7 | W2 | ALL
Synthetic evaluation query set (query → gold chunk pairs) | Phase 1 — Development & Reproducibility | 2026-10-05 | 2026-10-09 | 5 | W3 | Shraddha
DVC tracking of raw corpus, processed chunks and indexes | Phase 1 — Development & Reproducibility | 2026-10-05 | 2026-10-08 | 4 | W3 | Shreesha
MLflow setup + experiment logging conventions | Phase 1 — Development & Reproducibility | 2026-10-05 | 2026-10-07 | 3 | W3 | Shreyank
Baseline multilingual embedding experiments (BGE-M3, E5, Qwen3, Granite) | Phase 1 — Development & Reproducibility | 2026-10-08 | 2026-10-15 | 8 | W3 | Shrey
Vector store setup + retrieval evaluation (Recall@k, MRR, nDCG, latency) | Phase 1 — Development & Reproducibility | 2026-10-12 | 2026-10-16 | 5 | W4 | Shrey
Intent / complexity classifier training (optional artifact) | Phase 1 — Development & Reproducibility | 2026-10-12 | 2026-10-16 | 5 | W4 | Shreesha
End-to-end RAG tutor harness (retrieve → mother-tongue generation) | Phase 1 — Development & Reproducibility | 2026-10-13 | 2026-10-17 | 5 | W4 | Shraddha
Phase-1 evaluation report + baseline model selection sign-off | Phase 1 — Development & Reproducibility | 2026-10-16 | 2026-10-18 | 3 | W4 | Shreyank
Register embedding model (+ classifier) in MLflow Model Registry | Phase 2 — Productionization & Deployment | 2026-10-19 | 2026-10-22 | 4 | W5 | Shraddha
FastAPI inference service (query + language → context, response, metadata) | Phase 2 — Productionization & Deployment | 2026-10-19 | 2026-10-27 | 9 | W5 | Shreyank
PyTest unit tests (embedding, ranking, language handling, classifier) | Phase 2 — Productionization & Deployment | 2026-10-23 | 2026-10-30 | 8 | W5 | Shrey, Shreesha
Model-risk & quality checks (cross-language bias, robustness, security) | Phase 2 — Productionization & Deployment | 2026-10-26 | 2026-11-02 | 8 | W6 | Shraddha
PyTest integration tests + edge cases (empty, code-mixed, OOD, long query) | Phase 2 — Productionization & Deployment | 2026-10-28 | 2026-11-01 | 5 | W6 | Shreyank
Multi-stage Dockerfile + image build and size optimization | Phase 2 — Productionization & Deployment | 2026-10-28 | 2026-11-03 | 7 | W6 | Shrey, Shreesha
GitHub Actions CI (lint → PyTest → build → push to registry) | Phase 2 — Productionization & Deployment | 2026-11-02 | 2026-11-06 | 5 | W7 | Shraddha
Deployment to reachable endpoint + CD step + live smoke test | Phase 2 — Productionization & Deployment | 2026-11-05 | 2026-11-08 | 4 | W7 | Shrey, Shreesha
Structured JSON request logging (query, lang, intent, scores, latency, version) | Phase 3 — Monitoring, Feedback & Governance | 2026-11-09 | 2026-11-12 | 4 | W8 | Shrey
Evidently drift monitoring config + alert thresholds | Phase 3 — Monitoring, Feedback & Governance | 2026-11-11 | 2026-11-16 | 6 | W8 | Shreesha
Observability dashboard (Grafana / Streamlit / Power BI) | Phase 3 — Monitoring, Feedback & Governance | 2026-11-13 | 2026-11-18 | 6 | W8 | Shreyank
Simulated production traffic generator + baseline reference window | Phase 3 — Monitoring, Feedback & Governance | 2026-11-14 | 2026-11-18 | 5 | W8 | Shraddha
Deliberate drift injection experiment (noise / model swap / topic shift) | Phase 3 — Monitoring, Feedback & Governance | 2026-11-17 | 2026-11-20 | 4 | W9 | Shraddha
Drift detection evidence capture + alert validation | Phase 3 — Monitoring, Feedback & Governance | 2026-11-19 | 2026-11-21 | 3 | W9 | Shreesha
Retraining / re-indexing trigger + MLflow model comparison | Phase 3 — Monitoring, Feedback & Governance | 2026-11-20 | 2026-11-24 | 5 | W9 | Shrey
Promote better version + redeploy via CI/CD + evidence log | Phase 3 — Monitoring, Feedback & Governance | 2026-11-23 | 2026-11-25 | 3 | W10 | Shrey, Shreesha, Shraddha
Model card + governance / limitations report | Phase 3 — Monitoring, Feedback & Governance | 2026-11-18 | 2026-11-26 | 9 | W9 | Shreyank
Final report compilation + rubric traceability matrix | Phase 3 — Monitoring, Feedback & Governance | 2026-11-23 | 2026-11-27 | 5 | W10 | Shreyank
Demo rehearsal + live/recorded demonstration | Phase 3 — Monitoring, Feedback & Governance | 2026-11-26 | 2026-11-29 | 4 | W10 | ALL
Duration and Week are formulas. Week counts 7-day blocks from the project start date of 21/09/2026, which the user specified. Dates are inclusive of both endpoints and include weekends.

## Phase Summary
Phase | Weeks | Start Date | End Date | Tasks | Total Task-Days
Phase 1 — Development & Reproducibility | Weeks 1-4 | 2026-09-21 | 2026-10-18 | 12 | 66
Phase 2 — Productionization & Deployment | Weeks 5-7 | 2026-10-19 | 2026-11-08 | 8 | 50
Phase 3 — Monitoring, Feedback & Governance | Weeks 8-10 | 2026-11-09 | 2026-11-29 | 11 | 54
Total |  |  |  | 31 | 170
Task-days count calendar days per task and overlap across parallel tasks, so the total exceeds the 70-day project span.